## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Conduct a patient session | A patient needs a session, so a sessions needs to be scheduled, opened, notes have to be added to the session and the session needs to be closed | high |  | 6h | 0h | waiting
2 | Prescribe medication to patient | In a session, a doctor needs to prescribe medication to a patient. While adding the prescription, allergies and availability of the medication are checked | high | 10h | 10h | 0h | waiting
3 | Display patient information | On the patient site, display all available information on the patient. Allow certain information to be changed and custom notes to be added to the patient | medium | 3h |  | 0h | waiting
4 | Generate reports | Reports need to be generated based on patients, doctors and the organisation as a whole | low | 4h | 4h | 0h | waiting
5 | Integration of external systems | External systems such as the medical database, the medical expert system and the ERP of the organisation have to be integrated into the system and display information where applicable. | low | 10h | 10h | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Patient Session; Patient | Create patient class and dependencies | Database | Meyer | high
1.2 | 1 | Doctor | Create Doctor class and dependencies | Database | Meyer | high
1.3 | 1 | Session & session state | Implement state pattern | Model, controller | Seiler | high
1.4 | 1 | Session save & load | Load and save a Session | Database | Meyer | high
1.5 | 1 | Session memento | implement memento Pattern | Model, controller | Fränzi | medium
1.6 | 1 | Patient selection | Show patient information | UI | Bregi | low
1.7 | 1 | Patient session information | Show patient session information | UI | Bregi | low
1.8 | 1 | Memento pattern design | Prepare Presentation for Memento pattern | - | Simon | high
1.9 | 1