## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Conduct a patient session | A patient needs a session, so a sessions needs to be scheduled, opened, notes have to be added to the session and the session needs to be closed | medium | 6h | 6h | 0h | waiting
2 | Prescribe medication to patient | In a session, a doctor needs to prescribe medication to a patient. While adding the prescription, allergies and availability of the medication are checked | high | 10h | 10h | 0h | waiting
3 | Display patient information | On the patient site, display all available information on the patient. Allow certain information to be changed and custom notes to be added to the patient | low | 3h | 450h | 0h | waiting
4 | Generate reports | Reports need to be generated based on patients, doctors and the organisation as a whole | low | 4h | 4h | 0h | waiting
5 | Integration of external systems | External systems such as the medical database, the medical expert system and the ERP of the organisation have to be integrated into the system and display information where applicable. | medium | 10h | 10h | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | high | 8 | 6 | 5 | work in progress