## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Conduct a patient session | A patient needs a session, so a sessions needs to be scheduled, opened, notes have to be added to the session and the session needs to be closed | high | 33h | 42h | 37h | Done
2 | Prescribe medication to patient | In a session, a doctor needs to prescribe medication to a patient. While adding the prescription, allergies and availability of the medication are checked | high | 26.5h | 25h | 16h | Work In Progress
3 | Display patient information | On the patient site, display all available information on the patient. Allow certain information to be changed and custom notes to be added to the patient | medium | 7h | 8h | 6h | Work In Progress
4 | Generate reports | Reports need to be generated based on patients, doctors and the organisation as a whole | low |  |  | 0h | waiting
5 | Integration of external systems | External systems such as the medical database, the medical expert system and the ERP of the organisation have to be integrated into the system and display information where applicable. | low |  |  | 0h | waiting
0 | Generic Software Engineering | General software engineering tasks such as environment setup, navigation, Unit tests | critical | 20h | 18h | 5.5h | Work In Progress

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original [h] | Effort Plan Updated [h] | Effort Actual [h] | Status
1.1 | 1 | Patient Session; Patient | Create patient class and dependencies | Database | Meyer | high | 2 | 2 | 2 | Done
1.2 | 1 | Doctor | Create Doctor class and dependencies | Database | Meyer | high | 2 | 2 | 2 | Done
1.3 | 1 | Session & session state | Implement state pattern | Model, controller | Seiler | high | 2 | 2 | 2 | Done
1.4 | 1 | Session save & load | Load and save a Session | Database | Meyer | high | 2 | 2 | 1 | Done
1.5 | 1 | Session memento | implement memento Pattern | Model, controller | Fränzi | medium | 4 | 3 | 3 | Cancelled
1.6 | 1 | Patient selection | Show patient information | UI | Bregi | low | 5 | 6 | 4 | Continued in Sprint 2
1.7 | 1 | Patient session information | Show patient session information | UI | Bregi | low | 5 | 8 | 6 | Continued in Sprint 2
1.8 | 1 | Memento pattern design | Prepare Presentation for Memento pattern | - | Simon | high | 1 | 1 | 2 | Done
1.6 | 2 | Patient selection | Show patient information | UI | Bregi | high | 5 | 6 | 5 | Done
1.7 | 2 | Patient session information | Show patient session information | UI | Bregi | high | 5 | 10 | 10 | Done
2.1 | 2 | Allergy Database | Create DB table and entities for Allergies | Database | Meyer | high | 0.5 | 0.5 | 0.5 | Done
2.2 | 2 | Test Data for development | Create test data for database (all databases) with patients, allergies, medicine, ingredients, a few sessions and doctors | Database | Meyer | medium | 2 | 2 | 2 | Done
2.3 | 2 | MedicationService | Create the entity of the MedicationService. | Model | Seiler | high | 7.5 | 6 | 5 | Done
2.4 | 2 | Medication prescription | Show a dialog to perform the medication prescription | UI | Fränzi | medium | 6 | 6 | 2 | Continued in Sprint 3
0.1 | 2 | Code documentation | Add commentary as requested by the teacher | - | Simon | low | 2 | 2 | 2 | Done
2.5 | 2 | Test Data for development | Compile a list of medication, ingredients, allergies as preparation for task 2.2 | - | Meyer | high | 0.5 | 0.5 | 0.5 | Done
0.2 | 2 | Basic GUI, navigation between pages | Figure out navigation for Vaadin Framework | UI | Meyer | low | 3 | 1 | 1 | Done
2.6 | 2 | Search function | Implement a search function to allow search for patients and sessions | UI,Controller,DB | Seiler | low | 2 | 2 | 3 | Done
2.7 | 2 | Change Session state | Modify the session view to allow the user to change the session state to another | UI | Bregi | medium | 2 | 2 | 1 | Done
3.1 | 2 | Show patient overview | Show all available information about a patient | UI | Simon | medium | 2 | 2 | 1 | Continued in Sprint 3
3.2 | 2 | Create note for patient | Allow the user to create a note for a patient and for a session | Controller,UI | Meyer | low | 2 | 2 | 4 | Done
0.3 | 2 | MobileGUI | Migrate all existing views to MobileGUI | UI | Meyer | high | 2 | 2 | 2.5 | Done
2.4 | 3 | Medication prescription | Show a dialog to perform the medication prescription | UI | Fränzi | medium | 6 | 6 | 2 | Work In Progress
3.1 | 3 | Show patient overview | Show all available information about a patient | UI | Simon | medium | 2 | 3 | 1 | Work In Progress
0.4 | 3 | Unit Tests MedicalService | Mock datasource and Unit Tests for medical prescription | Tests | Seiler | high | 6 | 6 | 0 | Work In Progress
0.6 | 3 | Unit Tests SessionState | Unit tests for correct session state transitions and permissions | Tests | Meyer | high | 1 | 1 | 0 | Work In Progress
3.3 | 3 | Create note for session | Allow the user to add a note to a session | Controller,UI | Bregi | low | 1 | 1 | 0 | Work In Progress
0.5 | 3 | GUI Streamlining | General GUI streamlining, best effort | UI | Meyer | high | 6 | 6 | 0 | Work In Progress
4.1 | 3 | Report all patients | Allow the doctor to generate a report with all patients and the number of treatments / prescription per patient | Controller | [5 empty] | Waiting
4.2 | 3 | Report medication | Allow the doctor to generate a report with all available medication, ingredients and known sideeffects | Controller | [5 empty] | Waiting