## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Conduct a patient session | A patient needs a session, so a sessions needs to be scheduled, opened, notes have to be added to the session and the session needs to be closed | high | 20h | 30h | 22h | Work In Progress
2 | Prescribe medication to patient | In a session, a doctor needs to prescribe medication to a patient. While adding the prescription, allergies and availability of the medication are checked | high | 35h | 35h | 0h | waiting
3 | Display patient information | On the patient site, display all available information on the patient. Allow certain information to be changed and custom notes to be added to the patient | medium |  |  | 0h | waiting
4 | Generate reports | Reports need to be generated based on patients, doctors and the organisation as a whole | low |  |  | 0h | waiting
5 | Integration of external systems | External systems such as the medical database, the medical expert system and the ERP of the organisation have to be integrated into the system and display information where applicable. | low |  |  | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Patient Session; Patient | Create patient class and dependencies | Database | Meyer | high | 2h | 2h | 2h | Done
1.2 | 1 | Doctor | Create Doctor class and dependencies | Database | Meyer | high | 2h | 2h | 2h | Done
1.3 | 1 | Session & session state | Implement state pattern | Model, controller | Seiler | high | 2h | 2h | 2h | Done
1.4 | 1 | Session save & load | Load and save a Session | Database | Meyer | high | 2h | 2h | 1h | Done
1.5 | 1 | Session memento | implement memento Pattern | Model, controller | Fränzi | medium | 4h | 3h | 3h | Cancelled
1.6 | 1 | Patient selection | Show patient information | UI | Bregi | low | 5h | 6h | 4h | Continued in Sprint 2
1.7 | 1 | Patient session information | Show patient session information | UI | Bregi | low | 5h | 8h | 6h | Continued in Sprint 2
1.8 | 1 | Memento pattern design | Prepare Presentation for Memento pattern | - | Simon | high | 1h | 1h | 2h | Done
1.6 | 2 | Patient selection | Show patient information | UI | Bregi | high | 5h | 6h | 4h | Work In Progress
1.7 | 2 | Patient session information | Show patient session information | UI | Bregi | high | 5h | 8h | 6h | Work In Progress
2.1 | 2 | Allergy Database | Create DB table and entities for Allergies | Database | Meyer | high | 0.5h | 0h | 0h | Done
2.2 | 2 | Test Data for development | Create test data for database (all databases) with patients, allergies, medicine, ingredients, a few sessions and doctors | Database | Meyer | medium | 2h | 2h
2.3 | 2 | MedicationService | Create the entity of the MedicationService. | Model | Seiler | high | 7.5h | 7.5h
2.4 | 2 | Medication prescription | Show a dialog to perform the medication prescription | UI | Meyer | medium | 6h | 6h
0.5 | 2 | Code documentation | Add commentary as requested by the teacher | - | Simon | low | 2h | 2h
2.5 | 2 | Test Data for development | Compile a list of medication, ingredients, allergies as preparation for task 2.2 | - | Fränzi | high | 0.5h | 0.5h